## Sheet1
Bug ID | Description/Summary | Test Title | Test Steps | Expected Result | Actual Result | Severity | Priority | Comment
Bug ID_001 Register | User does not receive a confirmation email after registering, preventing password reset. | Validate A link to set a new password will be sent to registered email | 1.Navigate to the registration page. 2.Enter valid details and submit the form. 3.Check the registered email for a confirmation link. | A confirmation email should be sent to the registered email | User has not received any email to their registered email. | Critical | P0 | Email system verification needed.
Bug ID_002 Register | Special characters in account details are not displayed correctly after registration. | Validate registration with one special character | 1.Navigate to the registration page. 2.Enter special characters in name or password fields. 3.Submit the form. | System should show a validation error | User got logged in but in account detail special characters are not displayed correctly. | Major | P0 | Input validation issue.
Bug ID_003 Register | Register button is enabled by default instead of being disabled initially. | Validate registration button disabled initially | 1.Navigate to the registration page. 2.Observe the Register button without entering any details. | Register button should be disabled. | It is enabled by default. | Minor | P3 | UI issue, needs correction.
Bug ID_004 Register | System does not sanitize input properly, leading to XSS vulnerabilities. | Validate registration with XSS attack script | 1.Navigate to the registration page. 2.Enter an XSS script in any input field. 3.Submit the form. | System should sanitize input and prevent XSS. | Please include an '@' in the email address error appears. | Critical | P0 | Security vulnerability.
Bug ID_005 Register | Error messages do not disappear even after correcting an invalid email. | Validate error clearing when correcting long email entry | 1.Navigate to the registration page. 2.Enter an invalid email and submit. 3.Correct the email and check if the error disappears. | Error messages should disappear once corrected. | After correcting email, the error message is not disappearing. | Major | P0 | Form validation issue.
Bug ID_006 Logout | The system does not display a confirmation prompt before logging the user out. | Validate that the system asks for confirmation before logging out | 1.Navigate to the Shopease website. 2.Login with valid credentials. 3.Click on the "Logout" button. | A confirmation prompt should appear before the user is logged out. | No confirmation prompt appears, and the user is logged out immediately. | Major | P1 | Missing confirmation prompt before logging out may lead to accidental session termination.
Bug ID_007 Search | The search functionality does not handle case insensitivity properly, affecting user experience. | Validate that the Case Insensitivity in Search | 1.Ensure a product named "Kitchen" exists in the product catalog. 2.Enter "kitchen" in lowercase into the search box. 3.Perform the search. | The search should return "Kitchen" regardless of case differences. | The search results display items in lowercase "kitchen" instead of maintaining original casing. | Major | P1 | Case insensitivity should be properly handled to provide an accurate and user-friendly search experience.
Bug ID_008 Search | The search bar does not provide auto-suggestions, impacting usability and making it difficult for users to find products efficiently. | Validate that Auto-Suggestion in Search Box | 1.Ensure that auto-suggestion is enabled in the search bar. 2.Start typing "Smart Watch" in the search box. 3.Observe if suggestions appear | The system should provide auto-suggestions based on the entered text. | No suggestions appear while typing in the search bar. | Major | P1 | The lack of auto-suggestions reduces the user experience, making product discovery less efficient.
Bug ID_009 Search | The Shopease platform does not provide an option to change the language, making it impossible to search for products in languages other than English. | Validate the Search with Different Languages | 1.Access the Shopease homepage. 2.Attempt to switch the website to Spanish. 3.Search for "Reloj inteligente" (smartwatch). | The system should allow users to switch languages and return relevant product results in the selected language. | No option to change the language on the website. Searching for "Reloj inteligente" returns no results. | Critical | P0 | The absence of a multilingual feature limits accessibility for non-English speakers.
Bug ID_010 Product display | The "Buy Now" button is missing from the product display page, preventing users from directly proceeding to checkout. | Validate Buy Now Button Functionality | 1.Navigate to the product display page. 2.Click on the "Buy Now" button. | Clicking on the "Buy Now" button should redirect the user to the checkout page. | The "Buy Now" button is completely missing, and users cannot quickly proceed to checkout. | Critical | P0 | The absence of a "Buy Now" button impacts the shopping experience and could lead to cart abandonment.
Bug ID_011 Product display | The product sharing options are missing on the product display page, preventing users from sharing products on social media platforms. | Validate Product Sharing Options | 1.Navigate to the product display page. 2.Look for the social media sharing buttons. 3.Click on the available share buttons | Social media share buttons should be present and allow users to share product links on different platforms. | No sharing option is visible on the product page. | Minor | P3 | Although not a critical issue, the absence of sharing options reduces user engagement and product visibility on social media.
Bug ID_012 Product display | The shipping and return policy details are missing on the product page, and there is no visible link redirecting users to the policy information. | Validate Shipping & Return Policy Details | 1.Navigate to the product display page. 2.Look for shipping & return policy details on the page. 3.Check for any link that redirects to the shipping & return policy. | The shipping and return policy should be clearly mentioned on the product page or should have a visible link directing users to the policy details. | The policy details are not displayed, and no link is available to access this information from the product page. | Major | P1 | This issue can cause confusion for customers regarding return and shipping terms, potentially leading to a poor user experience and increased support queries.
Bug ID_013 Product display | The product page takes an excessive amount of time to load, causing a significant delay in user interaction | Validate Performance of Product Page | 1.Navigate to the Shopease product display page. 2.Measure the page load time using browser developer tools or a performance monitoring tool. | The product page should load within 3 to 5 seconds for an optimal user experience. | The product page takes more than 30 seconds to load, which is significantly higher than the expected performance threshold. | Critical | P0 | This issue severely impacts user experience and engagement, potentially leading to higher bounce rates and lost sales.
Bug ID_014 Wishlist | when an unauthenticated user clicks on the "Add to Wish List" button, the product is added directly without any login prompt. | Validate Non-Logged-In Users Get a Login Prompt | 1.Navigate to the Shopease website. 2.Click on the "Add to Wish List" button for any product. | The system should prompt the user to log in before adding the product to the wish list. | The product is added to the wish list without prompting for login. | Critical | P0 | Issue needs urgent attention since it affects core user functionalitie
Bug ID_015 Wishlist | The Wishlist feature should prevent duplicate entries when a user attempts to add the same product multiple times. | Validate Adding the Same Product Twice Does Not Duplicate It | 1.Navigate to the Shopease website. 2.Ensure that a specific product is already in the wish list. 3.Click "Add to Wish List" again for the same product. | The system should prevent duplicate additions and display an appropriate message. Alternatively, it should update the quantity rather than adding a separate duplicate entry | The system allows duplicate entries for the same product instead of handling it correctly. | Medium | P2 | This issue affects overall wishlist functionality and user experience.
Bug ID_016 Wishlist | The wishlist functionality should allow users to sort products based on various criteria. | Validate Sorting of Products in Wishlist | 1.Navigate to the Shopease website and go to the Wishlist page. 2.Attempt to sort products using available sorting options (Price, Date Added, or Name). | Products should be sorted correctly based on the selected sorting criteria. | Sorting functionality is missing in the Wishlist feature. | Minor | P3 | UX designers should ensure sorting is intuitive and accessible to users.
Bug ID_017 Wishlist | The wishlist icon (heart symbol) should dynamically update when a product is added to or removed from the wishlist. However, the icon does not change when the user adds or removes a product, causing confusion about the product's wishlist status. | Vaalidate the Wishlist Icon Updates When Adding/Removing Products | 1.Navigate to a product page. 2.Click the Wishlist (heart) icon to add the product to the wishlist. 3.Observe the icon to check if it updates (should be filled or highlighted). 4.Click the Wishlist icon again to remove the product from the wishlist. 5.Observe the icon to check if it returns to its default (unselected) state. | The wishlist icon should change dynamically based on the product's wishlist status: Filled/highlighted when added Unfilled/normal when removed | The wishlist icon does not update after adding or removing the product. Users cannot visually confirm if the product was successfully added/removed. | Medium | P2 | Developers should check if the issue is due to UI lag, missing event triggers, or API response delays.
Bug ID_018 Account Functionality | The password reset functionality should allow users to reset their password by requesting a reset email. However, when the user enters a registered email and submits the request, no password reset email is received. | Validate Password Reset Functionality | 1.Navigate to the Shopease login page. 2.Click on the ‘Lost your password?’ link. 3.Enter a registered email address and submit the request. 4.Check the email inbox (including spam/junk folders) for the password reset email. | The user should receive a password reset email with a link to reset their password. | No password reset email is received, even after multiple attempts. | Critical | P0 | Developers should review logs and error messages to identify why the reset email is not sent.
Bug ID_019 Address Book | The Shopease platform should allow users to set a saved address as the default for future orders. However, there is no "Set as Default" option available in the Address Book section, preventing users from selecting a preferred address. | Validate Setting an Address as Default | 1.Log in to the Shopease account. 2.Navigate to My Account > Address Book. 3.Identify an address and look for the “Set as Default” option. 4.Try to set an address as the default. | The system should allow the user to set an address as default, and it should be marked as the default address for future orders. | There is no “Set as Default” option available, preventing users from selecting a primary address. | Major | P1 | Developers should check if the option is missing due to UI limitations or backend restrictions.